## Agile Sprint Backlog
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 6 | DAY 5 | SPRINT REVIEW
User Story #1 | 8
Task |  |  |  | 7 | 5 | 3 | 0 | 0 | 10 | 0 | 0
Task |  |  |  | 3 | 1 | 1 | 5 | 0 | 5 | 1 | 0
Task |  |  |  | 1 | 0.5 | 0 | 3 | 0 | 6 | 0 | 0
Task |  |  |  | 0.5 | 1 | 2 | 3 | 1 | 4 | 0 | 0
User Story #2 | 1
Task |  |  |  | 3 | 3 | 0.5 | 0.5 | 0 |  | 0 | 2
Task |  |  |  | 3 | 5 | 5 | 1 | 1 |  | 1 | 0
Task |  |  |  | 2 | 2 | 5 | 0 | 1 |  | 0 | 1
Task |  |  |  | 5 | 5 | 9 | 5 | 1 |  | 0 | 1
User Story #3
DeliveryLocationsIndicater/TruckLocation | 8 | Abdullah Alramyan | completed | 10 hours | 2 | 2 | 2 | 2 | 2 | 13 | 0
Task |  |  |  | 3 | 1 | 3 | 3 | 3 |  | 0 | 0
Task |  |  |  | 1.5 | 1 | 0.5 | 0.5 | 1 |  | 1 | 0
Task |  |  |  | 2 | 0.5 | 0 | 0 | 0 |  | 0 | 3
User Story #4 | 8
Task |  |  |  | 9 | 4 | 2 | 2 | 1 |  | 1 | 0
Task |  |  |  | 6 | 6 | 3 | 3 | 3 |  | 1 | 1
Task |  |  |  | 6 | 2 | 8 | 8 | 1 |  | 0 | 1
Task |  |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | 0 | 0
User Story #5 | 3
Task |  |  |  | 2 | 1 | 1 | 1 | 0.5 |  | 1 | 1
Task |  |  |  | 6 | 6 | 6 | 0.5 | 3 |  | 9 | 0
Task |  |  |  | 9 | 9 | 9 | 4 | 3 |  | 3 | 3
Task |  |  |  | 0.5 | 0.5 | 0.5 | 1 | 0.5 |  | 0 | 1
TOTAL |  |  |  | 70 | 56 | 61 | 43 | 22 | 27 | 31 | 14

## Agile Sprint Backlog - BLANK
AGILE SPRINT BACKLOG TEMPLATE WITH BURNDOWN CHART
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #1
Task
Task
Task
Task
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0